## STUDENT PORTAL
TASK | STATUS | DEV COMMENTS | TEST COMMENTS
Application for Admission. | Done |  | Add fields for Profile Pic,Attach Required Documents
Checking for application status. | DONE |  | Notification on Email incase of status change
Acceptance / Declining of admission. | Done |  | Okay
Term / Session registration. | Done |  | Add function for optional services
Access and download of assignments / carry home assessment / homework. | Done |  | Okay
Online Submission of assignments. | Done |  | Need for Resubmitting
Viewing, downloading and printing of examination results. | Partial | Viewing completed, printing and downloading in progress
Payment of various fees through mobile money, debit cards, bank deposit. | Not done | Joseph and Albert to follow up on Bank integration
Viewing, downloading and printing of unofficial and official transcript. | Partial | Viewing completed, printing and downloading also completed
Request for transport and transport cancellation. | Done |  | Okay
Viewing, downloading and printing of statement of accounts. | Partial | Viewing completed, printing and downloading in progress | Add Totals
Entering of comments on errors or complaints on the student statement of account. | Not done
Appointment scheduling with instructor / mentor. | Not done | To be completed by today
Clearance form. | Done | Functionality working
Event / Trip Registration. | Done | Done
Student customer relationship management; allowing students to make requests, complaints and suggestions online. - | Not d | Completed
Student time table. | Interfaces done | To be completed by today
School calendar of events. | Done
Hostel accommodation request. | Done

## INSTRUCTORS PORTAL
TASK | STATUS | DEV COMMENTS | TEST COMMENTS
Uploading of assignments. | Done |  | Filter Exams per lecturer units
Downloading of submitted assignments. | Done |  | Filter Exams per lecturer units
Recording of examination results. | Done |  | 1.Add a field for remarks. 2. Filter Exams per lecturer units
Leave application. | Done
Transport Request. | Done
Training request. | Done
Instructors time table. | Be done by today
Imprest / Advance request. | Done
Loan application. | Done
Purchase requisition. | Done
Store requisition. | Done
Performance appraisal. | Pending
School calendar of events. | Done
Claims. | Done

## STAFF PORTAL
TASK | STATUS | DEV COMMENTS | TEST COMMENTS
Leave application. | Done
Training request. | Done
Transport Request. | Done
Training Request. | Done
Imprest / Advance request. | Done
Loan application. | Done
Purchase Requisition. | Done
Store requisition. | Done
Claims. | Done
Performance appraisal. | Pending