## Sheet1
Task Code | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Comments | % Complete
2001 | St Mary's School | 6 days | Mon 11/1/16 | Mon 18/1/16 |  |  |  | 0%
2001-01 | Student Finance | 1 day | Tue 12/1/16 | Tue 12/1/16 |  |  |  | 0%
2001-01-001 | Batch Emailing of Student Statement | 1 day | Tue 12/1/16 | Tue 12/1/16 |  | Jacob |  | 0%
2001-01-002 | Notification Through SMS (URL to be provided) | 1 day | Tue 12/1/16 | Tue 12/1/16 |  | Jacob |  | 0%
2001-02 | Payroll | 4 days | Tue 12/1/16 | Fri 15/1/16 |  |  |  | 0%
2001-02-001 | After the Loan is Stopped/Expires the deduction should stop. Currently it continues to the next month | 1 day | Tue 12/1/16 | Tue 12/1/16 |  | Jacob |  | 0%
2001-02-002 | Payslip format to fit A4 (fit two employees on the same page) | 1 day | Tue 12/1/16 | Tue 12/1/16 |  | Jacob |  | 0%
2001-02-003 | Gratuity and arrears calculation (Formular to be provided) | 1 day | Thu 14/1/16 | Thu 14/1/16 |  | Jacob |  | 0%
2001-02-004 | Salary Increament as a percentage and as an amount | 1 day | Thu 14/1/16 | Thu 14/1/16 |  | Jacob |  | 0%
2001-06 | NAV Exams | 1 day | Mon 18/1/16 | Mon 18/1/16 |  |  |  | 0%
2001-06-001 | Juniour School Exams results (Report Form) | 1 day | Mon 18/1/16 | Mon 18/1/16 |  | Jacob |  | 0%
2005 | C. Dormans/Sangana | 51 days | Mon 7/12/15 | Wed 24/2/16 |  |  |  | 0%
2005-01 | Value Addition | 51 days | Mon 7/12/15 | Wed 24/2/16 |  |  |  | 0%
2005-01-001 | Development of Value Addition processes/bulking functionality prototype | 10 days | Mon 7/12/15 | Fri 18/12/15 |  | Jacob |  | 0%
2005-01-002 | Review of Value addition processes prototype with Ecom/Sangana project team | 2 days | Wed 9/12/15 | Thu 10/12/15 |  | Jacob |  | 0%
2005-01-003 | Addressing issues arising from review of Value Addition processes/bulking functionality prototype | 15 days | Fri 11/12/15 | Mon 11/1/16 |  | Jacob |  | 0%
2005-01-004 | Review of Value Addition | 1 day | Wed 13/1/16 | Wed 13/1/16 |  | Jacob |  | 0%
2005-01-005 | Direct purchase | 5 days | Tue 12/1/16 | Mon 18/1/16 |  | Jacob |  | 0%
2005-01-006 | Review of Direct Purchase functionality with ECOM | 1 day | Mon 18/1/16 | Mon 18/1/16 |  | Jacob |  | 0%
2005-01-007 | Addressing issues arising from review of Direct purchase functionality. | 2 days | Tue 19/1/16 | Wed 20/1/16 |  | Jacob |  | 0%
2005-01-008 | Go-live | 3 days | Mon 8/2/16 | Wed 10/2/16 |  | Jacob¦Client |  | 0%
2005-01-009 | Post Implementation support | 10 days | Thu 11/2/16 | Wed 24/2/16 | 51 | Jacob |  | 0%